Getting Better Data From Our Pharmacies

We’ve built a shortage prediction system using national NHS data. It works — but it doesn’t know what’s selling in our own pharmacies. Connecting our dispensing data would make the alerts specific to us, not just the national average.

Option 1 — Manual Export (1–2 weeks, no IT needed)

Someone at each pharmacy exports their dispensing history as a spreadsheet — every system can do this. We load it in, run the analysis. Quick to test, costs nothing. Good enough to prove the concept.

Option 2 — Automated Monthly Pull (4–6 weeks, needs IT)

IT sets up a read-only connection to each pharmacy system’s database. Data pulls automatically every month — no one has to do anything manually. This is the right step once the pilot works.

Option 3 — Live Integration (3–6 months, development project)

A real-time feed from all pharmacies into a central system. Scales across any number of sites and opens the door to automating buying decisions. Bigger investment but it’s what turns this into a commercial product.

Recommendation: start with Option 1 at two or three pharmacies. If it works as expected, Option 2 is a standard IT task. Option 3 is a separate business case when we’re ready to scale.